## Brew & Grind Gantt
Brew & Grind Project Gantt Chart
Project Start 3/26/26 |  |  | Current Focus WBS + Budget |  |  | Final Due 5/6/26 |  |  | Completed |  |  | In Progress |  |  | Milestone |  |  | Phase
Phase | Task | Start | End | Days | Status | March 2026 | [5 empty] | April 2026
 | time axis 2026-03-26 to 2026-05-06
 | time axis 2026-03-26 to 2026-05-06
Planning | Planning Phase | 2026-03-26 | 2026-04-18 | 24 | Phase | bar: 2026-03-26 to 2026-04-18
Planning | Team Charter | 2026-03-26 | 2026-03-27 | 2 | Completed | bar: 2026-03-26 to 2026-03-27
Planning | Project Charter | 2026-03-27 | 2026-03-29 | 3 | Completed | bar: 2026-03-27 to 2026-03-29
Planning | Scope Statement | 2026-03-29 | 2026-03-30 | 2 | Completed | bar: 2026-03-29 to 2026-03-30
Planning | WBS Development | 2026-03-30 | 2026-04-16 | 18 | Completed | bar: 2026-03-30 to 2026-04-16
Planning | Budget / Cost Estimation | 2026-04-10 | 2026-04-18 | 9 | Completed | bar: 2026-04-10 to 2026-04-18
Milestone | ◆ Planning Complete | 2026-04-18 | 2026-04-18 | 1 | Milestone | bar: 2026-04-18
Development | Development Phase | 2026-04-18 | 2026-04-26 | 9 | Phase | bar: 2026-04-18 to 2026-04-26
Development | Website Planning | 2026-04-18 | 2026-04-19 | 2 | Completed
Development | Website Wireframe | 2026-04-19 | 2026-04-20 | 2 | Completed | bar: 2026-04-19 to 2026-04-20
Development | Content Creation | 2026-04-20 | 2026-04-23 | 4 | Completed | bar: 2026-04-20 to 2026-04-23
Development | Branding (logo, colors) | 2026-04-20 | 2026-04-22 | 3 | Completed | bar: 2026-04-20 to 2026-04-22
Development | Website Build | 2026-04-23 | 2026-04-25 | 3 | Completed | bar: 2026-04-23 to 2026-04-25
Development | Website Testing | 2026-04-25 | 2026-04-26 | 2 | Completed
Milestone | ◆ Website Complete | 2026-04-26 | 2026-04-26 | 1 | Milestone | bar: 2026-04-26
Finance | Finance Phase | 2026-04-20 | 2026-04-27 | 8 | Phase | bar: 2026-04-20 to 2026-04-27
Finance | Cost Breakdown | 2026-04-20 | 2026-04-22 | 3 | Completed | bar: 2026-04-20 to 2026-04-22
Finance | Revenue Forecasting | 2026-04-21 | 2026-04-23 | 3 | Completed | bar: 2026-04-21 to 2026-04-23
Finance | NPV Calculation | 2026-04-23 | 2026-04-24 | 2 | Completed | bar: 2026-04-23 to 2026-04-24
Finance | ROI Calculation | 2026-04-24 | 2026-04-25 | 2 | Completed | bar: 2026-04-24 to 2026-04-25
Finance | Payback Analysis | 2026-04-25 | 2026-04-26 | 2 | Completed
Milestone | ◆ Financials Complete | 2026-04-27 | 2026-04-27 | 1 | Milestone | bar: 2026-04-27
Report | Report Phase | 2026-04-27 | 2026-05-02 | 6 | Phase | bar: 2026-04-27 to 2026-05-02
Report | Introduction Section | 2026-04-27 | 2026-04-28 | 2 | Completed | bar: 2026-04-27 to 2026-04-28
Report | Business Background | 2026-04-28 | 2026-04-29 | 2 | Completed | bar: 2026-04-28 to 2026-04-29
Report | Weekly Tasks Write-up | 2026-04-29 | 2026-04-30 | 2 | Completed | bar: 2026-04-29 to 2026-04-30
Report | Gantt + WBS Integration | 2026-04-30 | 2026-05-01 | 2 | Completed | bar: 2026-04-30 to 2026-05-01
Report | Appendix Screenshots | 2026-05-01 | 2026-05-01 | 1 | Completed | bar: 2026-05-01
Report | Editing & Formatting | 2026-05-01 | 2026-05-02 | 2 | Completed | bar: 2026-05-01 to 2026-05-02
Milestone | ◆ Report Complete | 2026-05-02 | 2026-05-02 | 1 | Milestone | bar: 2026-05-02
Presentation | Presentation Phase | 2026-05-02 | 2026-05-05 | 4 | Phase | bar: 2026-05-02 to 2026-05-05
Presentation | Slide Creation | 2026-05-02 | 2026-05-03 | 2 | Completed
Presentation | Design & Branding Slides | 2026-05-03 | 2026-05-04 | 2 | Completed | bar: 2026-05-03 to 2026-05-04
Presentation | Practice Presentation | 2026-05-04 | 2026-05-05 | 2 | Completed | bar: 2026-05-04 to 2026-05-05
Presentation | Final Adjustments | 2026-05-05 | 2026-05-05 | 1 | Completed | bar: 2026-05-05
Milestone | ◆ Final Submission | 2026-05-05 | 2026-05-05 | 1 | Milestone | bar: 2026-05-05
Phase | Calendar Days |  |  |  |  | 2026-03-31: This Gantt chart includes all required phases: planning, development, financial analysis, report writing, and presentation. Completed work, current work, future work, and milestones are all organized in one clean view.
Planning | 24 | bar: 2026-03-31 to 2026-05-06
Development | 9 | bar: 2026-03-31 to 2026-05-06
Finance | 8 | bar: 2026-03-31 to 2026-05-06
Report | 6
Presentation | 4